## Goldrush Checklist
Month | Category | Task | AI Support | How AI Can Help | Status | Notes
June | Kickoff | Confirm project objective, success criteria, and required in-service date with owner | Assist | I can draft the objective statement, milestone summary, and meeting agenda.
June | Operating Philosophy | Confirm normal utility operation philosophy | Assist | I can draft the operating narrative and review for gaps.
June | Operating Philosophy | Confirm generator synchronization to energized bus philosophy | Assist | I can draft synchronization sequence language and checklist items.
June | Operating Philosophy | Confirm utility-parallel operation philosophy | Assist | I can document the mode logic and operating assumptions.
June | Operating Philosophy | Confirm island operation during utility outage philosophy | Assist | I can draft the sequence narrative and edge-case review.
June | Operating Philosophy | Confirm underfrequency load shedding philosophy | Assist | I can structure the UFLS basis and restoration logic notes.
June | Operating Philosophy | Confirm controlled return-to-utility philosophy | Assist | I can draft the transfer-back sequence and hold points.
June | Operating Philosophy | Confirm tie breaker operating philosophy and transfer sequence requirements | Assist | I can turn assumptions into a clean review checklist.
June | Commercial / Scope | Confirm final scope split between HEE, SEL, CAT, contractor, and owner | Assist | I can build a responsibility matrix and identify overlaps/gaps.
June | Commercial / Scope | Confirm SEL supply scope for two SEL-700G relays and one RTAC | Handle | I can draft and revise the formal scope request language.
June | Commercial / Scope | Confirm SEL engineering support allowance and obtain quote | Assist | I can draft the quote request and clarify deliverables/exclusions.
June | Document Control | Collect one-lines, relay settings, RTAC files, CAT ECS-200 documents, comms drawings, SCADA point lists, panel drawings, and IP lists | Assist | I can make a document request checklist and tracker.
June | Document Control | Create controlled document list and revision log | Handle | I can build and maintain the revision log template.
June | Engineering Input | Identify missing information required before detailed engineering begins | Assist | I can turn the current package into an RFI / missing-info list.
June | Engineering Input | Issue RFI list for missing technical information | Handle | I can draft the RFI document and organize it by discipline.
June | Field Verification | Confirm field equipment actually installed at mains, tie, generators, and RTAC integration points | Assist | I can prepare the verification checklist and photo log format.
June | Field Verification | Confirm available VT inputs, VSYNC inputs, breaker status points, close paths, trip paths, and spare I/O | Assist | I can build the field verification sheet.
June | Field Verification | Verify whether main and tie SEL-751 relays will be used for synchronizing supervision | Assist | I can summarize the decision criteria and assumptions.
June | Field Verification | Confirm exact RTAC model, communication ports, protocol requirements, and expansion needs | Assist | I can convert vendor data into a clean requirement list.
June | Basis of Design | Develop Basis of Design document | Handle | I can draft the document from the proposal and your inputs.
June | Basis of Design | Review Basis of Design with owner and key vendors | Assist | I can prepare agenda, discussion points, and redline summary.
June | Basis of Design | Resolve comments and freeze operating philosophy | Assist | I can consolidate comments and produce the revised issue.
July | Detailed Design | Develop detailed control narrative for each sequence and operating mode | Handle | I can draft the narrative in engineering document form.
July | Detailed Design | Define permissives, initiators, aborts, and fail states for each sequence | Assist | I can structure them into a cause/effect or sequence table.
July | Detailed Design | Define generator breaker close supervision logic | Assist | I can help write the logic description and review completeness.
July | Detailed Design | Define main breaker synchronizing logic requirements | Assist | I can convert requirements into checklist/table format.
July | Detailed Design | Define tie breaker synchronizing and transfer logic requirements | Assist | I can document sequence assumptions and special cases.
July | Detailed Design | Define blocked-close reasons and operator indication requirements | Assist | I can build a blocked-reason matrix and alarm list.
July | Controls Interface | Define generator start, stop, availability, and lockout interfaces with CAT controllers | Assist | I can draft the interface matrix and open questions list.
July | Detailed Design | Develop preliminary cause-and-effect matrix | Handle | I can create the matrix spreadsheet.
July | I/O | Develop detailed I/O list for control, status, analog, alarms, UFLS, and communications points | Handle | I can build and maintain the I/O spreadsheet.
July | I/O | Define point naming standard and final point list structure | Handle | I can propose and format the naming convention.
July | Communications | Develop communications architecture diagram and interface summary | Assist | I can draft the interface summary and diagram notes.
July | Communications | Confirm relay-to-RTAC, RTAC-to-SCADA, RTAC-to-SEL-3530, and CAT communications protocols | Assist | I can compile the protocol matrix and decision log.
July | Communications | Define Mirrored Bits usage if applicable | Assist | I can help document the use cases and signals.
July | Communications | Define DNP3 / SCADA mapping requirements | Assist | I can structure the mapping workbook and point categories.
July | Communications | Define event, SOE, and alarm retention requirements | Assist | I can draft the retention / reporting requirements section.
July | Schematics | Develop schematic markups for control additions, sync references, and marshalling | Assist | I can review and annotate markup packages, but not replace CAD drafting.
July | Schematics | Confirm utility-side and alternate-bus sync reference wiring requirements | Assist | I can build the checklist and design assumptions list.
July | Hardware / Panels | Confirm panel space, mounting arrangement, wiring routes, and termination strategy | Assist | I can prepare the field walkdown checklist.
July | Hardware / Panels | Confirm network switch, fiber, serial, or Ethernet accessory needs | Assist | I can build the accessory list and quote checklist.
July | Procurement | Review procurement requirements for long-lead items | Assist | I can flag long-lead risk items and tracking columns.
July | Procurement | Release final equipment list for procurement | Handle | I can compile the final list into a clean issue-for-procurement format.
July | Procurement | Track SEL quote, lead time, and submittal turnaround | Handle | I can maintain the tracker and draft follow-ups.
July | Procurement | Review vendor submittals for hardware correctness and application fit | Assist | I can review submittal content and summarize technical gaps.
July | Procurement | Resolve submittal comments quickly to avoid schedule erosion | Assist | I can consolidate comments and draft response language.
July | Detailed Design | Freeze detailed design inputs before final relay and RTAC configuration | Assist | I can produce the freeze checklist and decision log.
August | Protection | Develop SEL-700G protection philosophy and settings basis for both generator positions | Assist | I can draft the settings basis document and review structure.
August | Protection | Build draft settings files for both SEL-700G relays | Assist | I can help structure settings sheets and review logic, but final relay settings need engineering judgment.
August | Protection | Update applicable SEL-751 settings and logic for mains, tie, and supporting feeders | Assist | I can support review and documentation of changes.
August | RTAC | Develop RTAC database, communication mappings, tags, and point structure | Assist | I can help organize tags, points, and naming consistency.
August | RTAC | Develop RTAC supervisory control logic for sequencing, synchronization, parallel, island, UFLS, restoration, and alarms | Assist | I can draft logic narratives, truth tables, and test cases.
August | HMI | Build HMI screens for overview, generator status, breaker/sync status, UFLS, alarms, comms health, and operating mode | Assist | I can draft screen content and layout notes.
August | HMI | Develop operator controls, permissions, and command interlocks in HMI/RTAC | Assist | I can build the control philosophy and permissions checklist.
August | Testing | Build FAT / bench test checklist | Handle | I can create the full checklist and expected results matrix.
August | Testing | Simulate sequence transitions offline and document results | Assist | I can capture and organize simulation results and exception logs.
August | Testing | Verify ready-to-sync, blocked-close, utility loss, islanding, UFLS, return-to-utility, and alarm behavior | Assist | I can build structured test scripts and witness sheets.
August | QA / Revision | Correct logic gaps, naming issues, mapping errors, and sequencing conflicts | Assist | I can review revisions and keep the issue log current.
August | QA / Revision | Update drawings, I/O lists, and point lists to match programmed logic | Handle | I can update controlled lists and revision notes.
August | QA / Revision | Prepare controlled issue package for field installation and checkout | Handle | I can assemble the package index and issue set.
August | QA / Revision | Confirm all required engineering files are backed up and version-controlled | Assist | I can build the backup checklist and archive index.
September | Receiving | Confirm delivery of SEL relays, RTAC, accessories, and communication hardware | Assist | I can create the receiving checklist and discrepancy log.
September | Receiving | Inspect equipment for damage, correctness, and completeness | Assist | I can provide the inspection form and punch item template.
September | Field Readiness | Confirm latest approved files are loaded into field issue package | Handle | I can verify the issue set and revision status.
September | Field Readiness | Coordinate outage windows, access requirements, and site work schedule | Assist | I can draft the coordination checklist and schedule summary.
September | Field Readiness | Confirm contractor labor plan and division of responsibility for panel work and wiring | Assist | I can build the responsibility matrix.
September | Installation | Install RTAC, relays, accessories, and communication hardware | Assist | I can support with installation checklists, not physical installation.
September | Installation | Complete panel modifications and marshalling terminations | Assist | I can help track completion and punch items.
September | Installation | Land control wiring, status wiring, communications wiring, and sync reference circuits | Assist | I can provide QC checklists and turnover sheets.
September | Installation QA | Verify polarity, labeling, terminal identification, and wire-by-wire continuity | Assist | I can create the QC checklist.
September | Installation QA | Confirm breaker control paths and trip paths are correctly wired and isolated | Assist | I can draft the verification procedure.
September | Installation QA | Verify VT and synchronizing reference wiring at each applicable relay | Assist | I can provide the witness checklist.
September | Communications Checkout | Verify network communications between SEL devices and existing automation systems | Assist | I can build the communication checkout sheet.
September | Checkout | Perform point-to-point checkout for every critical point | Assist | I can create the point-to-point checkout workbook.
September | Checkout | Confirm status points indicate correctly in RTAC/HMI | Assist | I can structure the test record sheets.
September | Checkout | Confirm control outputs operate correctly in safe test condition | Assist | I can help write the functional test form.
September | Checkout | Confirm alarms map correctly to operator displays and remote systems | Assist | I can build the alarm verification log.
September | Checkout | Confirm sequence permissives reflect actual field states | Assist | I can prepare the permissive validation matrix.
September | Checkout | Confirm event records, SER, and oscillography retrieval paths work properly | Assist | I can create the verification checklist.
September | Punch List | Resolve installation deficiencies before live commissioning begins | Assist | I can maintain the punch list and closure tracker.
September | Punch List | Update punch list daily and assign owner for each open item | Handle | I can maintain that tracker continuously.
September | Pre-Commissioning | Verify all prerequisites for commissioning are complete | Handle | I can build the commissioning readiness checklist.
October | Commissioning | Finalize commissioning test plan and obtain owner approval | Handle | I can draft and revise the test plan package.
October | Commissioning | Confirm CAT, SEL, HEE, contractor, and owner witness availability | Assist | I can build the witness matrix and schedule list.
October | Commissioning | Confirm site is operationally ready and safe for live testing | Assist | I can create the readiness checklist.
October | Commissioning | Perform protection testing for both SEL-700G relays | Assist | I can prepare procedures and record sheets, but not execute field testing myself.
October | Commissioning | Perform testing on modified SEL-751 functions | Assist | I can support test scripts and documentation.
October | Commissioning | Verify RTAC logic operation in staged commissioning sequence | Assist | I can provide sequence-by-sequence witness sheets.
October | Commissioning | Verify communications to SCADA and existing SEL-3530 | Assist | I can build the comms verification matrix.
October | Commissioning | Verify generator start sequence logic | Assist | I can structure the test script.
October | Commissioning | Verify synchronization permissives and close logic | Assist | I can build the functional checkout form.
October | Commissioning | Perform live or simulated synchronization testing as site conditions allow | Assist | I can document procedures and results.
October | Commissioning | Verify generator parallel operation | Assist | I can provide the witness checklist and result log.
October | Commissioning | Verify load sharing interface expectations with CAT controls | Assist | I can capture acceptance criteria and issue log.
October | Commissioning | Verify utility loss response and islanding behavior | Assist | I can build the scenario checklist.
October | Commissioning | Verify UFLS stages operate and restore correctly | Assist | I can provide staged test sheets.
October | Commissioning | Verify blocked-reason handling and operator visibility | Assist | I can create the validation record.
October | Commissioning | Verify return-to-utility sequence and transfer behavior | Assist | I can structure the witness log and exception list.
October | Commissioning | Retest corrected deficiencies and close commissioning punch items | Assist | I can maintain retest and closure tracking.
October | As-Left Documentation | Confirm final settings files and RTAC project files match as-left condition | Assist | I can organize the as-left file register.
October | As-Left Documentation | Export and archive final relay settings, RTAC logic, HMI files, point lists, and IP documentation | Handle | I can build the archive index and closeout binder structure.
October | As-Left Documentation | Mark up and finalize as-built drawings | Assist | I can help track markups and revision notes.
October | Closeout | Compile test reports, commissioning records, and exception log | Handle | I can compile and format the closeout package.
October | Closeout | Deliver owner closeout package | Handle | I can prepare the package transmittal and final checklist.
October | Training | Conduct owner training on architecture, modes, alarms, HMI use, troubleshooting, and support handoff | Assist | I can build the training outline, slides, and handouts.
October | Closeout | Obtain owner acceptance or conditional acceptance | Assist | I can draft the acceptance form and punch-list language.
October | Closeout | Confirm remaining post-startup action items, responsible parties, and due dates | Handle | I can create the final action register.
October | Closeout | Close the project or transition to warranty / support phase by October 31 | Assist | I can prepare the turnover summary and support transition checklist.
Weekly | Project Management | Hold weekly project status review and update action log | Handle | I can generate the agenda, action log, and summary every week.
Weekly | Project Management | Update schedule against October 31 target | Handle | I can maintain the schedule tracker and recovery notes.
Weekly | Project Management | Track procurement status and long-lead risk | Handle | I can maintain the procurement tracker.
Weekly | Project Management | Track open RFIs, submittals, and technical decisions | Handle | I can maintain those logs.
Weekly | Project Management | Track programming completion percent during August | Assist | I can help quantify progress against the task list.
Weekly | Project Management | Track installation completion percent during September | Assist | I can help structure the completion metrics.
Weekly | Project Management | Track punch list closure rate during September and October | Handle | I can maintain the punch metrics.
Weekly | Project Management | Maintain risk register with mitigation actions | Handle | I can build and update the risk register.
Weekly | Project Management | Maintain document revision log | Handle | I can manage the revision log.
Weekly | Project Management | Record major decisions and approval dates | Handle | I can maintain the decision log.
Weekly | Project Management | Keep final acceptance criteria visible so scope does not drift | Assist | I can maintain the acceptance checklist and reminders.
Hold Point | Critical Controls | Do not start final relay/RTAC programming until Basis of Design is approved | Handle | I can keep this as a formal gate in the tracker.
Hold Point | Critical Controls | Do not release field issue drawings until I/O, sync references, and communications architecture are confirmed | Handle | I can maintain this release gate.
Hold Point | Critical Controls | Do not mobilize commissioning until point-to-point checkout is substantially complete | Handle | I can keep the readiness gate checklist current.
Hold Point | Critical Controls | Do not declare completion until final files, test reports, and owner training are finished | Handle | I can maintain the final completion gate.

## Legend
Status | Meaning
Not Started | Task has not begun
In Progress | Task is actively being worked
Blocked | Task cannot proceed yet
Complete | Task is finished
Deferred | Task is intentionally postponed
AI Support | Meaning
Handle | I can draft, organize, track, or produce most of the deliverable directly
Assist | I can support with drafting, review, checklists, logs, or coordination, but field / engineering judgment / execution remains with the team

## Loop Philosophy
Topic | Guidance
Purpose | Use loops mainly for supervisory sequencing and state management, not fast machine control.
Use in RTAC | Sequence/state evaluation for generator start, sync requests, breaker close permissives, utility-parallel operation, island transitions, and return-to-utility transitions.
Use in RTAC | Retry, timeout, and alarm escalation logic when commanded steps do not complete in time.
Use in RTAC | Communications and device-health watchdog monitoring for relays, RTAC, CAT controls, and SCADA interfaces.
Use in RTAC | UFLS restoration checks based on staged permissives and readiness.
Use in RTAC | Continuous operator feedback for blocked-close reasons, active permissives, sequence progress, and abnormal conditions.
Do Not Use in RTAC | Fast synchronization control.
Do Not Use in RTAC | Generator load sharing control.
Do Not Use in RTAC | Voltage / VAR closed-loop control.
Do Not Use in RTAC | Speed / frequency regulation.
Recommendation | Keep real-time machine control in the Caterpillar ECS-200 / generator controls with relay-supervised close logic. Use the RTAC as the supervisory state machine.